## Sheet1
EVM All Sprints
Metric | Value | Unit |  | Metric | Calculate
EV (Earned Value) | 5580 | GBP |  | EV | PV to date * RP
PV (Planned Value) | 5580 | GBP |  | PV
AC (Actual Cost) | 5580 | GBP |  | AC
|  |  |  | CV | EV-AC
CV (Cost Variance) | 0 | GBP |  | SV | EV-PV
SV (Schedule Variance) | 0 | GBP |  | CPI | EV/AC
|  |  |  | SPI | EV/PV
CPI (Cost Performance Index) | 1 |  |  | BAC
SPI (Schedule Performance Index) | 1 |  |  | EAC | BAC/CPI
|  |  |  | VAC | BAC-EAC
BAC (Budget at Completion) | 5580 | GBP
EAC (Estimate at Completion) | 5580 | GBP
VAC (Variance at Completion) | 0 | GBP
Total Planned Story Points | 203
Total Planned Hours | 372
Yearly Salary | 30000
Hourly Rate | 15 | (£30000/52 weeks/40 hours)
Daily Rate | £15*4 = £60 | Each day counts as 4 hours
Cost per Point | (372*15)/203=£27.49 per point
Team Member | Units Contributed | Cost Contribution (£60/unit)
Raiyan | 34 | 2040
Neel | 26 | 1560
Samuel | 15 | 900
Sanil | 18 | 1080
Total | 93 | 5580
Sprint | Dates | PV (£) | AC (£) | Points | Cost/Point
Sprint 1 | 12 Nov - 03 Dec | 1860 | 1860 | 35 | 53.14
Sprint 2 | 04 Dec - 18 Dec | 1800 | 1800 | 40 | 45
Sprint 3 | 19 Dec - 25 Dec | 1020 | 1020 | 58 | 17.59
Sprint 4 | 26 Dec - 01 Jan | 900 | 900 | 70 | 12.86
TOTAL | All Sprints | 5580 | 5580 | 203 | 27.49
The table above shows that as the project progressed, the Cost per Story Point decreased significantly showing that
we as a team became more efficient over time as each Sprint went by
Overall, there was a 75% reduction in Cost per Point from the first to the last Sprint.