## COCOMO I and II
COCOMO I
Organic development context used for all because it is a small, command line music player application | [5 empty] | Organic | a | b | c | d
[6 empty] | Values | 2.4 | 1.05 | 2.5 | 0.38
EAF Cost Drivers | Value Given | Reason
RELY | 1.15 | High quality is required with no acceptable bugs or failures
DATA | 1 | Nominal
CPLX | 1.15 | Audio engine, seeking, and queue logic require high complexity
TIME | 1 | Nominal
STOR | 1 | Nominal
PVOL | 1 | Nominal
PCON | 1 | Nominal
ACAP | 1 | Nominal
DOCU | 1 | Nominal
PCAP | 1 | Nominal
AEXP | 1 | Nominal
SITE | 1 | Nominal
LTEX | 0.95 | Team's good experience with Python lowers the language effort.
TOOL | 0.91 | Mandatory use of PyCharm and GitHub provides high efficiency.
SCED | 1.1 | Compressed, one and a half month schedule increases effort intensity.
Total EAF = | 1.2576
File name | LOC | KLOC | E (Without EAF) | D (Without EAF) | P (Without EAF
__init__
audio_backend.py | 250 | 0.25 | 0.55982 | 2.0054 | 0.27916
main.py | 400 | 0.4 | 0.91701 | 2.419 | 0.37908
player_core.py | 250 | 0.25 | 0.55982 | 2.0054 | 0.27916
player_queue.py | 550 | 0.55 | 1.2811 | 2.7468 | 0.46641
player_state.py | 100 | 0.1 | 0.2139 | 1.3913 | 0.15374
playlists_basic.py | 525 | 0.525 | 1.2201 | 2.6963 | 0.4525
player_metrics.py | 100 | 0.1 | 0.2139 | 1.3913 | 0.15374
Final Results
Overall Sprint 1 without EAF | 2175 | 2.175 | 5.4268 | 4.7541 | 1.1415
Overall Sprint 1 with EAF | 2175 | 2.175 | 6.8249 | 5.1868 | 1.3158
COCOMO II
Scale Factor | Value Given | Reason
PREC | 3.72 | Norminal
FLEX | 3.04 | Nominal
RESL | 4.24 | Norminal
TEAM | 2.19 | High, because a small 4 person SCRUM team with the use of GitHub with equal number of story points
PMAT | 6.24 | Low, because it is a short student project with not yet fully defined processes.
Total SF = | 19.43
Size (s) = | 2.175
Scale Factors = | 19.43
Effort Multiplier = | 1.2576
Constants = | a = 2.4, b = 1.05 | (Organic Mode)
E = | 7.9372 | Person-Months
D = | 5.493 | Months
P = | 1.4449 | Developers