## Sheet1
EVM Sprint 4
Metric | Value | Unit | Metric | Calculate
EV (Earned Value) | 900 | GBP | EV | PV to date * RP
PV (Planned Value) | 900 | GBP | PV
AC (Actual Cost) | 900 | GBP | AC
|  |  | CV | EV-AC
CV (Cost Variance) | 0 | GBP | SV | EV-PV
SV (Schedule Variance) | 0 | GBP | CPI | EV/AC
|  |  | SPI | EV/PV
CPI (Cost Performance Index) | 1 |  | BAC
SPI (Schedule Performance Index) | 1 |  | EAC | BAC/CPI
|  |  | VAC | BAC-EAC
BAC (Budget at Completion) | 900 | GBP
EAC (Estimate at Completion) | 900 | GBP
VAC (Variance at Completion) | 0 | GBP
Total Planned Story Points | 70
Total Planned Hours | 60
Yearly Salary | 30000
Hourly Rate | 15 | (£30000/52 weeks/40 hours)
Daily Rate | £15*4 = £60 | Each day counts as 4 hours
Cost per Point | (60*15)/70=£12.86 per point
Team Member | Units Contributed | Cost Contribution (£60/unit)
Raiyan | 5 | 300
Neel | 5 | 300
Samuel | 2 | 120
Sanil | 3 | 180
Total | 15 | 900